## CM
New client onboarding checklist (internal)
Info required | Priority ( 1-5) | Request sent to client? |  | Status/Notes | Info received? (link to documents is appropriate) | Responsible | Accountable | Consulted | Informed
| 1 - a MUST. 3 Nice to have, ongoing 5. Can come at a later date | Date sent | By whom?
Information Management
Create a client folder in the client folder and move all assets/info/background information to it from 'potential client' folder | 1 |  |  |  | S:\2013 | New Business | New Business |  | Campaign Manager/Head of Campaign Management
Promote company from a 'lead' or 'prospect' on Synergist to a client. Ensure all client contacts and contact details are on Synergist as well as details of any meetings and sales notes | 1 |  |  |  |  | New Business | New Business |  | Campaign Manager/Head of Campaign Management
Handover meeting with CM/Head of Production/Client relations/ Head of Design/ Copy/ HTMLConsultant/New business rep ( as appropriate) | 1 |  |  |  |  | New Business | New Business |  | Campaign Manager/Head of Campaign Management/Head of Production/Production team leaders
Key client contacts received ( who is day to day contact for production jobs) | 1 |  |  |  |  | New Business | New Business |  | Campaign Manager/Head of Campaign Management
Account Mangement
Commercial
Initial proposal signed off by client | 1 |  |  |  |  | New Business | New Business |  | Head of Campaign Management/COO/Head of Production
Client contract signed off? | 2 |  |  |  |  | COO | COO |  | Head of Campaign Management/COO
NDA signed off? | 3 |  |  |  |  | COO | COO |  | Head of Campaign Management/COO
Billing details - name, address, telehone number, email address of person the invoice should be sent to. ( accounts payable) Also require escalation details of who we should contact if we have any invoice queries | 1 |  |  |  |  | New Business | New Business |  | Finance/Georgia. Campaign Manager
Are PO's required? PO received for first project | 1 |  |  |  |  | New Business | New Business |  | Finance/Georgia/ Campaign Manager
As we progress with first project and after completed first project review commercial arrangements - does the SOW accurately reflect the work we did/are doing. CM to meet with production and consultants to review | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Head of Consulting/ New Business | COO
Administration
Create RACI document including all details of project that need to be completed | 4 |  |  |  |  | Campaign Manager | Head of Campaign Management | Production team leaders/Consultants | Campaign Manager/Head of Campaign Management/Head of Production/Production team leaders
CM/ CE/ escalation details communicated to client | 1 |  |  |  |  | Head of Campaign Management | Head of Campaign Management
Set up Client alias email address | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management
Set up client with a sharefile account and send details to client | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management
CM induction presentation given | 3 |  |  |  |  | Senior Campaign Manager | Head of Campaign Management
All briefing documentation created and shared with client before first project briefed in ( eg client mailing brief/ CRF) | 1 |  |  |  | ..\..\..\production\campaign_manager\process\internal\Client_mailing_brief.docx | Campaign Manager | Head of Campaign Management | EDS Team leader
Calendar of mailings received? | 2 |  |  |  |  | Campaign Manager | Head of Campaign Management |  | EDS Team leader
Introduction email and telephone call from CM (outlining next steps/use of sharefile/escalation process) | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management
Project timelines sent to Client (general timinings of set tasks explained, such as set up and test and build time) | 2 |  |  |  | timeline_template_vs-actual.xlsx | Campaign Manager | Head of Campaign Management
Client WIP created for ongoing day to day project management | 2 |  |  |  |  | Campaign Manager | Senior Campaign Manager |  | Consultant
Weekly status call established | 3 |  |  |  |  | Campaign Manager | Head of Campaign Management | Consultant
Monthly meeting established | 3 |  |  |  |  | Campaign Manager | Client Relationship Director | Consultant
Client/production process written up | 3 |  |  |  |  | Campaign Manager/Head of Production | Head of Production | All production team leaders | Head of Campaign Management
Client Relations
Client onboarding meeting set up and given | [5 empty] | Client Relations | Client Relationship Director | Consultant/ CM/ Head of Production/ Head of CM | New Business
Quarterly strategy review meeting established | 3 |  |  |  |  | Client Relations | Client Relationship Director | Consultant | Head of Campaign Management / Consultant
Performance SLA process established | 3 |  |  |  |  | Client Relations | Client Relationship Director | Consultant | Head of Campaign Management
Production
Design ( if required)
Completed mailing brief received | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Design/HTML/Copy teams | Design/HTML/Copy teams
Brand Guidelines | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Design | Design
High res version of logo | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Design | Design
Colours ( RGB or Hexidecimal) | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Design | Design
Examples of previous emails | 2 |  |  |  |  | Campaign Manager | Head of Campaign Management | Design/copy/html | Design/copy/html
Fonts ( actual file or name so we can source) | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Design | Design
Does the design need to be optimised for mobile readership? | 2 |  |  |  |  | Campaign Manager | Head of Campaign Management | Head of Creative Services | Head of Creative Services
Copy ( if required)
Completed mailing brief received | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Head of Copy | Head of Copy
Tone of voice guidelines | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Head of Copy | Head of Copy
Examples of previous emails | 2 |  |  |  |  | Campaign Manager | Head of Campaign Management | Head of Copy | Head of Copy
HTML ( if required)
Examples of assets that will be supplied for us to build ( eg PSD) (if we are not designing) | 2 |  |  |  |  | Campaign Manager | Head of Campaign Management | Head of Creative Services | Head of Creative Services
Details of link tracking ( third party tools/web analytics/ platform tracking) | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Head of Creative Services | Head of Creative Services
Any HTML build specifics ( eg need to add headers and footers to PSD's) | 2 |  |  |  |  | Campaign Manager | Head of Campaign Management | Head of Creative Services | Head of Creative Services
Does the HTML build need to be optimised for mobile readership? | 2 |  |  |  |  | Campaign Manager | Head of Campaign Management | Head of Creative Services | Head of Creative Services
Mobile testing? Is this required? - All new clients campaigns are tested on mobile as standard, please ensure QA team complete this | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Head of Creative Services/ QA | Head of Creative Services/ QA
Deployment/reporting ( if required)
EDS to appoint a deployment lead | 1 |  |  |  |  | Deployment team leader | Head of Production | Campaign Manager | Head of Campaign Management
Deliverability - confirm any deliverability issues seen in last 6 months( eg emails going into Gmail junk folders) | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Data team | EDS team leader/Head of Production
Confirm any input required from ESP and relevant timeframes (i.e. do they need 2 days to set up a new email address/folder) | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Data team | EDS team leader/Head of Production
Examples of assets that will be supplied for us to build ( eg PSD) (if we are not designing) | 2 |  |  |  |  | Campaign Manager | Head of Campaign Management |  | EDS team leader/Head of Production
ESP login details | 1 |  |  |  |  | Campaign Manager | Deployment team leader | Data team | EDS team leader/Head of Production
ESP support details | 3 |  |  |  |  | Campaign Manager | Deployment team leader | Data team | EDS team leader/Head of Production
Master CRF and deployment checklist created and completed | 1 |  |  |  |  | Deployment team leader | Head of Production | Data team
Data ¦ Import process ( Data upload method, database names, segments, data management, data schema) | 1 |  |  |  |  | Campaign Manager | Data team |  | EDS team leader/Head of Production
Data brief to be created if any data work is required | 1 |  |  |  |  | Campaign Manager | Data team | Data team | EDS team leader/Head of Production
Data personlisation ( default, salutation) | 1 |  |  |  |  | Campaign Manager | Head of Campaign Management | Data team | EDS team leader/Head of Production
FTP details ( if these are required) | 3 |  |  |  |  | Campaign Manager | Head of Campaign Management | Data team | EDS team leader/Head of Production
Unsubcribe details | 1 |  |  |  |  | Campaign Manager | Deployment team leader | Data team | EDS team leader/Head of Production
Confirm Envelope options/details (from address, friendly from name, reply to address, bounce address) | 1 |  |  |  |  | Campaign Manager | Deployment team leader | Data team | EDS team leader/Head of Production
Confirm Campaign Structure and mailing activities - (folder structure/campaign naming convention) | 1 |  |  |  |  | Campaign Manager | Deployment team leader | Data team | EDS team leader/Head of Production
Approval and seed lists agreed | 1 |  |  |  |  | Campaign Manager | Deployment team leader | Data team | EDS team leader/Head of Production
Complete compulsory spam filter tests for the first 3 sends | 1 |  |  |  |  | Testing team | Head of Production | Data team | Campaign Manager
Client specific QA process established, for example mobile ( please link in with the QA team to create this) | 3 |  |  |  |  | Testing team | Head of Production |  | Campaign Manager