## Checklist
New client onboarding checklist
Info required | Priority ( 1-5) | Request sent to client? |  | Status/Notes | Completed? | Responsible | Accountable | Consulted | Informed
| 1 - a MUST. 3 - Nice to have, ongoing 5 - Can come at a later date | Date sent | By whom? |  | Yes/No | Person responsible for ensuring task gets completed | Person accountable for ensuring tasks gets completed | People that need to be consulted in order to get tasks completed | People that should be informed regarding information collected and that task is completed
Pre-client coming onboard
If AW are required to join client pitch AW to be informed as soon as RFP is received. RFP sent to AW and a call set up to discuss | 1 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson) | AW Production Manager ( Andrea Shyrock) for US Clients only. For UK clients Production Director ( Katie Aston) | AW Head of Campaign Management (Claire Rollinson)
Silverpop to reach out to AW about client coming onboard when it reaches 50/75% probability of converting | 1 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson) | AW Head of campaign Management ( Claire Rollinson) | AW Production Manager ( Andrea Shyrock) / US Campaign Manager (Danielle Monaco) for US clients only
Pitch presentation completed by Silverpop, with AW feeding into any production type questions and who will service account from SP end | 2 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson) | AW Head of campaign Management ( Claire Rollinson) AW Production Manager ( Andrea Shyrock) for US Clients only.
Client onboarding
Once won, Silverpop to confirm and communicate client team ( product advisor/ account director/relationship manager, if applicable) | 1 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson)
Alchemy Worx to confirm CM team on account | 1 |  |  |  |  | AW Head of campaign Management ( Claire Rollinson) | AW Head of campaign Management (Claire Rollinson) |  | Silverpop, Partner Services Development Director (Paige Henderson) Julie Shand Smith for UK clients
Silverpop to send any notes gathered during the sales process, as well as any sample mailings and materials to Alchemy Worx. | 1 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) and Silverpop RM | Silverpop, Partner Services Development Director (Paige Henderson) | AW Head of campaign Management ( Claire Rollinson) AW Production Manager ( Andrea Shyrock) for US Clients only.
Handover meeting with Silverpop, AW and client as appropriate - discuss all work required, ways of working, what outstanding items of info we still require | 1 |  |  |  |  | Silverpop - Relationship Manager (existing accounts), Silverpop Regional Sales manager (new accounts), Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson) | AW Head of campaign Management ( Claire Rollinson) AW Production Manager ( Andrea Shyrock) for US Clients only ans Client, Silverpop AM for existing acounts. | AW Campaign Manager
Key client contacts received and sent to AW( who is day to day contact on client side) | 1 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson) | AW Head of campaign Management ( Claire Rollinson) AW Production Manager ( Andrea Shyrock) for US Clients only and Client | AW Campaign Manager
Client Calendar of mailings received from client | 2 |  |  |  |  | AW Campaign Manager | AW Campaign Manager |  | AW Head of campaign Management ( Claire Rollinson) AW Production Manager ( Andrea Shyrock) for US Clients only.
AW And Silverpop client team details and escalation details communicated to client | 1 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson) | AW Campaign Manager | AW Head of campaign Management ( Claire Rollinson)
Silverpop platform specific
Silverpop will alert AW if the new account IP is shared or unique. (no custom domains on a shared IP) | 2 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) and Silverpop RM | Silverpop, Partner Services Development Director (Paige Henderson) |  | AW Head of campaign Management ( Claire Rollinson) AW Production Manager ( Andrea Shyrock) for US Clients only.
Ask client number of Relationship Tables and programs they have in case number needs to be increased from default (10 is default quantity of each.) To change, open support ticket with provisioning. | 5 |  |  |  |  | AW Campaign Manager | AW Campaign Manager |  | Silverpop, Partner Services Development Director (Paige Henderson), if quantities are over 10
Work with client to determine sending domains. Once selected, send domain(s) in a support case to provisioning. Support case should include Client name, customer contact, customer contact phone, Pod, Org. Apllies to sending domains, customer domains, custom landing pages domains. | 1 |  |  |  |  | AW Campaign Manager | AW Campaign Manager
Are there Omniture or Coremetrics integrations? If so, a form is sent by sales to provisioning. | 5 |  |  |  |  | Silverpop sales person | Silverpop sales person |  | AW Campaign Manager, Silverpop, Partner Services Development Director (Paige Henderson)
Whitelisting/IP warm up process - 30 days. Allow 20 to 30 hrs | 1 |  |  |  |  | AW Campaign Manager | AW Campaign Manager | Client
Determine if additional IPs are needed. If so, alert Paige and Salesperson | 5 |  |  |  |  | AW Campaign Manager | AW Campaign Manager | Silverpop, Partner Services Development Director (Paige Henderson), if quantities are over 10 | Silverpop Sales
Enable support portal access for client and have password auto-emailed to client | 1 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson) |  | AW Campaign Manager, Client
FTP user creation. Determine if FTP users are needed. If needed, open support case. | 5 |  |  |  |  | AW Campaign Manager | AW Campaign Manager | Client
Commercial
Silverpop SOW sent to AW and signed off by both AW and Silverpop. Check SOW reflects work we feel we are undertaking | 1 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson) | AW Head of campaign Management ( Claire Rollinson) AW Production Manager ( Andrea Shyrock) for US Clients only. | AW Head of campaign Management ( Claire Rollinson) AW Production Manager ( Andrea Shyrock) for US Clients only.
Silverpop provides Order Form Number to Alchemy Worx. Order form numbe must be added to each project. | 1 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson) |  | AW Campaign Manager
Ensure client and all campaigns we are working on are on openair so we can log our time against each one. | 1 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson) | AW Head of campaign Management ( Claire Rollinson) AW Production Manager ( Andrea Shyrock) for US Clients only. | AW Campaign Manager
As we progress with first project and after completed first project review commercial arrangements - does the SOW accurately reflect the work we did/are doing. First project wash up meeting to be held with AW and Silverpop | 1 |  |  |  |  | AW Campaign Manager | AW Head of campaign Management ( Claire Rollinson) | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Relationship Manager/RSM /Account Director?
Administration/oneview
AW to set up client alias email address for all 'off oneview' communications | 1 |  |  |  |  | AW Campaign Manager | AW Head of campaign Management ( Claire Rollinson) |  | Client and all contacts on Silverpop client team
Silverpop to add that address to client record in Salesforce to ensure notifications reach the team | 1 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson) |  | AW Campaign Manager
Determine which client contacts need OneView access. Send client contact names and email addresses to Silverpop | 1 |  |  |  |  | AW Campaign Manager | AW Campaign Manager
Create oneview account for client | 1 |  |  |  |  | Silverpop, Partner Services Development Director (Paige Henderson) | Silverpop, Partner Services Development Director (Paige Henderson) |  | AW Campaign Manager
Oneview trainining set up with client. | 1 |  |  |  |  | AW Campaign Manager | Silverpop, Partner Services Development Director (Paige Henderson) | Client | AW Production Manager US ( Andrea) AW Head of Campaign Management, Silverpop, Partner Services Development Director (Paige Henderson)
Weekly status call established with client/AW and Silverpop | 3 |  |  |  |  | AW Campaign Manager | AW Head of campaign Management ( Claire Rollinson) | Sillverpop Relationship Manager and Client | AW Head of campaign Management ( Claire Rollinson) and Silverpop, Partner Services Development Director (Paige Henderson)?
AW to write up client/production process | 3 |  |  |  |  | Campaign Manager/Head of Production | Head of Production | All production team leaders | Head of Campaign Management
Production
If AW are building or populating HTML of an email the following will be required
Examples of assets that will be supplied for us to build HTML( eg., PSD) | 2 |  |  |  |  | AW Campaign Manager | AW Head of campaign Management ( Claire Rollinson) | Client, Silverpop?? | Silverpop??
Details of link tracking ( third party tools/web analytics/ platform tracking) | 1 |  |  |  |  | AW Campaign Manager | AW Head of campaign Management ( Claire Rollinson) | Client, Silverpop?? | Silverpop??
Any HTML build specifics ( eg., need to add headers and footers to PSD's) | 2 |  |  |  |  | AW Campaign Manager | AW Head of campaign Management ( Claire Rollinson) | Client, Silverpop?? | Silverpop??
Does the HTML build need to be optimised for mobile readership? | 2 |  |  |  |  | AW Campaign Manager | AW Head of campaign Management ( Claire Rollinson) | Client, Silverpop?? | Silverpop??
Mobile testing? Is this required? | 1 |  |  |  |  | AW Campaign Manager | AW Head of campaign Management ( Claire Rollinson) | Client, Silverpop?? | Silverpop??
Silverpop platform/mailing set up information required
Silverpop login details for AW to log into clients account | 1 |  |  |  |  | AW Campaign Manager to ask client | AW Head of campaign Management ( Claire Rollinson) | Client
Is a second or new org required? If yes, submit support case. | 5 |  |  |  |  | AW Campaign Manager | AW Campaign Manager | Client
FTP details ( if these are required) | 3 | [6 empty] | Client
MASTER SUPPRESSION LIST . In every Org creation, the MASTER SUPPRESSION LIST file is placed in the ‘private’ folder of the primary account user | 1 |  |  |  |  | Silverpop
Client / Silverpop to send examples of html assets that will be supplied to AW ( if AW are not building or populating HTML) | 1 |  |  |  |  | Client or Silverpop, Partner Services Development Director (Paige Henderson)
Data personlisation ( default, salutation) | 1 |  |  |  |  | AW Campaign Manager
Data ¦ Import process ( Data upload method, database names, segments, data management, data schema) | 1 |  |  |  |  | AW Campaign Manager
Confirm Envelope options/details (from address, friendly from name, reply to address, bounce address) | 1 |  |  |  |  | AW Campaign Manager
Confirm Campaign Structure and mailing activities - (folder structure/campaign naming convention) | 1 |  |  |  |  | AW Campaign Manager
Unsubcribe details ( client form/preference centre or Silverpop link) | 1 |  |  |  |  | AW Campaign Manager
Approval and seed lists agreed | 1 |  |  |  |  | AW Campaign Manager
Mailing set up - AW internal tasks
AW to create master CRF and deployment checklist created and completed | 1 |  |  |  |  | AW Campaign Manager
AW to create data brief to be created if any data work is required | 1 |  |  |  |  | AW Campaign Manager
AW to create Client specific QA process established for client | 3 |  |  |  |  | AW Campaign Manager
Note on A9: Paige Henderson: I moved this task and the one below into the onboarding phase from the pre-sales phase.
Note on A12: Paige Henderson: Is this for existing clients? For ne clients, there will not be much to handoff.